The Catalyst Model Playbook

The Catalyst Model Playbook

"Buy it and they will come."

A step-by-step guide for founding a Community Land Trust
from land purchase to first households

www.sovereignmisfitfarm.com

# Table of Contents

# Why the Catalyst Model

Waiting until you have 12 aligned households to buy land together is a recipe for paralysis. Too many opinions, too many timelines, too many financial situations. The founder model flips the script: one person (or one household) buys the land, establishes the legal structure, sets the culture, and invites others in.

The land is the proof of concept. Everything else follows.

This playbook walks you through every phase — from the personal readiness check to the moment you hand governance to the community council and become just another neighbor.

# Phase 1: Personal Readiness Check

## Before Anything Else

Before you search for land, buy a domain name, or tell anyone your idea — sit with these questions honestly. The founder role is financially exposed, emotionally demanding, and deeply lonely until the first household shows up.

### The Five Readiness Questions

1. Can I carry the land financially for 12-24 months alone? Assume zero household contributions for the first year. Mortgage, taxes, insurance, basic improvements — can you cover it without desperation?

2. Am I willing to live on the land myself? Catalysts who don't live on-site lose credibility fast. People need to see you in the mud before they'll trust you with their family's future.

3. Can I handle being the decision-maker AND the scapegoat? Early on, every decision is yours and every problem is your fault. That changes as the council forms, but months 1-6 are a solo act.

4. Do I have a clear, written vision I can share? Not a vague feeling — a document. Values, rules, financial model, governance structure. If you can't articulate it on paper, you can't attract aligned people.

5. Is my personal life stable enough for this? Starting a community during a divorce, job loss, or health crisis multiplies every pressure. This is not an escape from problems — it creates new ones.

# Phase 2: Legal Structure — The CLT

## Month 1-2

Form the Community Land Trust before you close on land. The CLT is a 501(c)(2) nonprofit that holds land in perpetual trust. You personally should never own the community's land — that creates a power dynamic you can never undo.

### Legal Checklist

- Form the nonprofit: File articles of incorporation with your state as a 501(c)(2) title-holding organization

- Draft bylaws: Board structure (min 3 members), voting procedures, membership criteria, land-use decisions

- Apply for tax exemption: IRS Form 1024 for 501(c)(2) status (takes 3-6 months)

- Draft ground lease template: 99-year ground lease giving households the right to build while the CLT retains land ownership

- Consult an attorney experienced in CLT or nonprofit real estate (budget $2,000-$5,000)

### The Catalyst's Financial Dilemma

Option A (Most Common): Catalyst loans purchase price to the CLT, secured by a promissory note. CLT repays as households join and pay buy-ins.

Option B: Catalyst donates the purchase price to the CLT. Tax-deductible once 501(c)(2) status is granted.

Option C: Group of founding households pool funds through the CLT before purchase.

# Phase 3: Find and Purchase Land

## Month 2-4

### Non-Negotiable Land Requirements

Water. Well, creek, pond, or municipal. In western states, verify water rights come with the deed. Everywhere: get a well flow test before closing.

Zoning. Must allow multiple dwelling units. Call the county planning office and describe "12 households on shared agricultural land."

Road Access. Legal, year-round access on a road wide enough for a fire truck (county requirement). Landlocked parcels with handshake easements are lawsuits.

Soil and Slope. Get a USDA soil survey report (free at websoilsurvey.sc.egov.usda.gov). Avoid steep grades, flood plains, rocky subsoil.

Septic Capacity. 12 households means 12 septic systems or a community system. Get a perc test. If the soil won't perc, you can't build.

### Budget Estimate: 30-Acre Purchase

| Item | Range | Notes |
| --- | --- | --- |
| Phase 1: Land + Site Prep | $240K–$385K | Land, closing, well, road, fencing |
| Phase 2: Community Hall + Farm (Year 2-3) | $190K–$310K | Community building, farm infrastructure, septics |
| TOTAL PROJECT COST | $430K–$695K | Two-phase development |
| CDFI Loan | $150K–$250K | at 3.5-5.5% |
| Conservation Easement Sale | $60K–$150K | one-time source |
| State Housing Trust Fund | $0–$100K | forgivable loan |
| USDA EQIP Grants | $15K–$50K | agricultural improvements |
| USDA Rural Development | $0–$50K | infrastructure funding |
| Subtotal (6 sources above) | $335K–$795K |  |
| Community Investment Notes | $50K–$100K | at 4% |
| Crowdfunding | $10K–$50K | individual donors |
| TOTAL CAPITAL STACK | $405K–$710K | all sources combined |
| Annual Debt Service | $12K–$23K | ongoing payment obligation |

### Due Diligence Checklist

- Title search — verify clear title, no liens, no competing claims

- Boundary survey — fence lines are not property lines

- Percolation test — confirm septic viability

- Well flow test (if existing) or drilling quotes (if not)

- County planning call — describe your intended use

- Soil survey — USDA Web Soil Survey report

- Utility quotes — electric, internet, phone

- Flood zone check — FEMA flood maps

- Environmental assessment — wetlands, endangered species, contamination

- Visit in the worst season — check drainage, mud, access in rain/snow

# Phase 4: Build the Minimum Viable Community

## Month 4-8

You don't need 12 households. You need 3. Three households is the tipping point where it stops feeling like "one person's project" and starts feeling like a community.

### Day One Infrastructure for 3 Households

- Working well with distribution to at least 3 home sites

- Power — grid connection or solar at each site

- All-weather road access from public road to each home site

- At minimum one functioning septic system (others can start with composting toilets)

- Gathering space — covered pavilion, pole barn, or large tent

- Staked home sites, marked common areas, signed ground leases

### Critical Warning: The First Three

Households 1-3 define the community's DNA more than any document ever will. If your first three include a chronic complainer, a freeloader, or someone who doesn't actually want community — that energy becomes permanent. Be selective. An empty home site is better than the wrong household.

# Phase 5: Grow Deliberately — 3 to 12

## Month 8-24

Once you have 3 functioning households, growth happens through application and council vote — not the founder's say-so.

### Growth Milestones

Households 4-6 — The Starter: Core infrastructure proven. New households see a working model. Catalyst's financial burden decreases as buy-ins arrive. Gardens producing. Community kitchen operational.

Households 7-9 — The Village: Governance transitions to council. Catalyst has one vote. Specialized roles emerge. Community starts generating income.

Households 10-12 — The Full Circle: All sites occupied. CLT financially self-sustaining. Catalyst's loan repaid or close. System runs without any single person being essential.

### The Household Buy-In Model

Each household pays a buy-in to the CLT when they join. This is NOT purchasing land — the CLT owns the land forever. The buy-in covers their share of infrastructure costs and goes toward repaying the founder's loan.

- Typical buy-in range: $5K–$10K (depends on total land cost and improvements)

- Monthly ground lease: $450–$550 (covers property taxes, insurance, maintenance fund)

- 99-year ground lease gives security of tenure without land ownership

# Phase 6: The Catalyst's Exit from Power

## Month 12-18

This is the part most founders get wrong. You built this thing. You carried the financial risk. You slept in a tent while the well was drilled. And now you have to give up control. Not because you failed — because you succeeded.

A community that can't function without its founder isn't a community. It's a cult of personality.

### Transition Timeline

Month 6-8: Form community council with all current households. Catalyst chairs initially but begins sharing decisions.

Month 8-12: Council takes over operational decisions — new household approvals, budget, land use. Catalyst retains a CLT board seat.

Month 12-18: Council elects its own chair. Catalyst becomes a regular household with one vote. Term limits apply to the board.

Month 18+: Community is self-governing. Catalyst's contribution is honored but doesn't grant ongoing authority. You're a neighbor now.

# Phase 7: Financial Sustainability

## Ongoing

A community that depends on donations or a single benefactor is fragile. The SMF model generates revenue from day one and reaches self-sufficiency by the time the circle is full.

### Revenue Streams

| Source | Monthly Est. | When |
| --- | --- | --- |
| Ground lease fees (per hh) | $450–$550/mo | From move-in |
| CSA subscriptions | $2,500–$5,000 | Year 2+ |
| Farm stand / market | $500–$2,000 | Season 1+ |
| Workshop fees | $500–$1,500 | Year 1+ |
| Agritourism / farm stays | $300–$1,000 | Year 2+ |
| Full circle total (12 hh at Year 5) | $122K–$277K | Stabilized annual revenue |
| Monthly cost per household | $770–$870/mo | Year 5 stabilized |

Ground lease fees alone (12 households x $500 average) cover property taxes, insurance, and a maintenance fund. Everything else is growth capital or founder loan repayment.

# Appendix: Quick-Reference Checklists

## Land Purchase Closing Checklist

- Title search complete — clear title confirmed

- Boundary survey completed and recorded

- Perc test passed for at least 3 sites

- Well flow test or drilling quote obtained

- County zoning confirmation in writing

- Environmental assessment clean

- Flood zone status verified (FEMA)

- Utility connection quotes received

- Road access legally confirmed (easement or frontage)

- Purchase agreement contingencies met

- CLT formed and ready to take title

- Attorney reviewed all closing documents

## New Household Onboarding Checklist

- Application reviewed and approved by council vote

- Background check completed

- Trial visit period completed (minimum 2 weeks recommended)

- Ground lease signed

- Buy-in payment received by CLT

- Home site assigned and staked

- Orientation to community rules, governance, and shared responsibilities

- Introduction to all existing households

- Sweat equity schedule agreed upon

—

Sovereign Misfit Farm — www.sovereignmisfitfarm.com

This document is open source. Copy it. Adapt it. Build your village.